## Copy of Sheet1
| Apr. |  |  |  | May |  |  |  | Jun.
Task Title | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Place Purchase Orders (Microscope, Motors, Polarizers?)
Begin refining code and cleaning circuit
Continue circuit refinement
Adjust code to ensure power supply is sufficient
Possible redesign depending on motor selection
Start training data collection
Finish redesign based on new motors (if arrived)
Complete training data collection
Team Check-in (4/17)
Prepare new iteration of device
Begin slides for Alcon + BME180
Work on Final Report
Finalize presentation slides
Continue working on final report
Brainstorm 2-min pitch (5/1)
Have class demo ready
Further develop prototype
Prep for event
UROP Symposium (5/16)
Team Assessment #3 (5/22)
Aim for fleshed-out prototype with custom housing
Final Symposium + Awards (6/5)
Final Report + Team Evaluations Due (6/12)
Buffer period / Project Wrap-up if needed

## Sheet1
|  | November |  |  |  |  | December |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
Task # | Task Title |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Discuss Potential Counting Technologies | bar: W1 to W4
2 | Discuss Initial Design Options | bar: W3 to December W4
3 | Develop Test / Analysis Methods | bar: December W3 to January W3
4 | Begin Initial Design Process | bar: December W3 to January W3
5 | Cost Analysis | bar: W3 to December W3
6 | Basic Prototype | bar: December W4 to March W1
7 | Present Prototype to Mentors | bar: March W1 to March W3
8 | Revise Prototype I | bar: March W2 to April W4
9 | Present Prototype II to Mentors | bar: April W4 to May W1
10 | Feedback | bar: May W1 to May W4
11 | Device Implementation in Live Production | bar: May W3 to June W2
12 | Decrease Cycle Time for Streamlining Improvements | bar: June W1 to June W4